## Slide 1: Progress Report 7 12-5-2021
“Real-Time Localization of Emergency Responders in Dynamic Lightning environments with a pocket-sized LiDAR enhanced RGB-Camera.”

## Slide 2: Progress Report 6
Outcomes of last meeting
Results
  ORB-slam3,LOAM,SSL-slam, LIC-Fusion
  Challenge
Plans for next weeks

## Slide 3: Outcomes of last meeting
Mathematics
  Go back to the fundamentals of signal analysis
  Using an UKF instead of an EKF saves time on tuning the initial covariance matrix.
Report Layout
  Use the recommended layout of the grading rubric for your literature report
  Use colors and symbols to exemplify figures
Planning
  Use a gain factor when planning tasks, use the actual time spent on a task as feedback to adjust this factor when necessary
  Plan from the bottom up

## Slide 4: Next meeting?

## Slide 5: Where is room for improvement?
Plan more from the bottom up,
The tasks I wanted to do were to long and therefore planning didn’t work -> I now plan my days in Hourly blocks.

## Slide 6: What went well?
Diversify my days
Switching occasionally from literature to doing some programming or recap of lectures made me more productive and happy

## Slide 7: Plan for the next weeks

## Slide 8: Results Week 1
Progress meeting

## Slide 9: Results Week 2
Meet with Joost Jeschke
Presentation in GEO ict practice meeting
Study at TU
Ask Oleg to do midterm in CSI meeting in April

## Slide 10: Results Week 3

## Slide 11: Results Week 4

## Slide 12: Results Week 5
Progress Meeting Wednesday 16:30